## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
| Today | 2018-03-06
Task Name | Start Date | End Date | Duration (Days) | Days (Completed) | Days (Remaining) | Complete (%)
Planning & Analysis | 2018-02-13 | 2018-03-12 | 27 | 21 | 6
Setting up Git environment and repository | 2018-02-13 | 2018-02-14 | 1 | 1 | 0 | 100%
Decide on a project management tool | 2018-02-13 | 2018-02-14 | 1 | 1 | 0 | 100%
Deciding on milestones | 2018-02-13 | 2018-02-19 | 6 | 6 | 0 | 100%
Getting familiar with Twitter API | 2018-02-18 | 2018-03-10 | 20 | 16 | 4 | 80%
Preperation of requirement document | 2018-03-05 | 2018-03-12 | 7 | 1 | 6 | 14.29%
Completion of Requirement Phase | 2018-03-12 | 2018-03-12
Design | 2018-03-01 | 2018-04-06 | 36 | 5 | 31 | 13.89%
Design of 1st user story | 2018-03-01 | 2018-03-06 | 5 | 5 | 0 | 100%
Design of 2nd user story | 2018-03-01 | 2018-03-06 | 5 | 5 | 0 | 100%
Design of 3rd user story | 2018-03-05 | 2018-03-15 | 10 | 1 | 9 | 10%
Prepartion of flask environment and standards on Pycharm | 2018-03-15 | 2018-03-18 | 3 | 0 | 3 | 0%
Other tools and software to be used to create the application | 2018-03-04 | 2018-04-06 | 33 | 2 | 31 | 6.061%
Completion of Design Phase | 2018-04-06 | 2018-04-06
Implemantation | 2018-04-07 | 2018-05-17 | 40 | 0 | 40 | 0%
Installing system enviroments | 2018-04-11 | 2018-04-27 | 15 | 0 | 15 | 0%
Creating & testing databases | 2018-04-15 | 2018-04-21 | 6 | 0 | 6 | 0%
Preparing test case procedures | 2018-04-29 | 2018-04-30 | 1 | 0 | 1 | 0%
Coding & compiling | 2018-04-13 | 2018-05-12 | 29 | 0 | 29 | 0%
Performing unit test for each method in the code | 2018-04-17 | 2018-05-17 | 30 | 0 | 30
Completion of Implemantation Phase | 2018-05-17 | 2018-05-17
Testing & Submission | 2018-05-14 | 2018-05-25 | 11 | 0 | 11 | 0%
User story testing | 2018-05-14 | 2018-05-20 | 6 | 0 | 6 | 0%
Automation | 2018-05-20 | 2018-05-25 | 5 | 0 | 5 | 0%
Final Submission of the Project | 2018-05-25 | 2018-05-25
Formulas:
End Date = [Start Date]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]
DESIGN
REQUIREMENTS
IMPLEMENTATION
TESTING